Lesson 8 Individual Worksheet: Project Risk Management

References: PMBOK Guide 6th Edition Part 1: 11 Project Risk Management

- List and describe the processes related to Risk Management.

They include the following:
Risk Management planning, identification, analysis, response planning, response implementation and monitoring risk on a project.

- State some reasons why projects have risks.

Here are some reasons:

- Uncertainty always exists no matter if it is an objective, an assumption so on and so forth.

- Time, cost and manpower are always limited and never unlimited

- Part of a project’s description is having a unique deliverable and thus never done before the same as before

- Complete the table with the Project Risk Management Processes and its Process Groups:

| Project Risk Management Process | Process Group |
| --- | --- |
| - Plan Risk Management - Identify Risk - Perform Qualitative Risk Analysis - Perform Quantitative Risk Analysis - Plan Risk Responses | Planning |
| - Implement Risk Responses | Execution |
| - Monitor Risks | Monitoring & Controlling |

- Explain the difference between individual project risk and overall project risk.

Individual Project Risk: A risk (an uncertain event or condition) that if occurs could either have a positive or negative effect on one or more project objectives. An example if is a key employee resigns.

Overall Project Risk: It is the effect of uncertainty on the overall project, the overall project risks are derived from all the combines risks combined. An example is if the project is too complex that it goes over the budget.

- What are some examples of Technical Risks in a project?

- The team not having insufficient technical knowledge or skills

- Hardware reliability issues

- Cybersecurity problems

- Explain what Stakeholder risk appetite is.

It refers to how much risk a stakeholder is willing to take on to pursue the project’s objective. High risk appetite meaning, willing to take a big risk for a bigger reward and the inverse for low-risk appetite

- State the differences between the Perform Qualitative Risk Analysis and the Perform Quantitative Risk Analysis.

| Qualitative | Quantitative |
| --- | --- |
| Subjective | Numerical and data-based |
| Based on expert’s judgements and experience | Uses statistical methods such as EMV |
| Faster to complete and requires less resources | Requires high-quality data and more time |

- Using example, explain the Risk Response Strategies for dealing with Threats.

| Response Strategies for dealing with Threats | Examples |
| --- | --- |
| - Avoid | Removing the cause of the risk by changing the project plan, such as extending the schedule to avoid overtime that could cause burnout |
| - Mitigate | Taking action to reduce the probability or impact, such as conducting more tests or choose a reliable supplier. |
| - Transfer | Giving the responsibility for managing the risk or financial impact to someone who is better at managing it. Typically involves a “premium” to the other party taking the risk. |
| - Accept | Acknowledging the risk but not taking any action, either because it’s low priority or by creating a contingency plan. |
| - Escalate | The threat is outside the scope of the project manager’s authority or the project manager’s authority. The threat is then escalated to the relevant party in the organization |

- What are the Risk Response Strategies for dealing with Opportunities?

- Exploit: Ensure the opportunity is realized

- Share: allocate ownership to a third party who is best able to capture the opportunity

- Enhance: Increase the probability and impact of the opportunity

- Escalate: An opportunity that would benefit the entire organization is escalated to senior management

- Accept: Acknowledging the opportunity but not actively pursuing it

- North Poly Ltd is planning to set up a number of web servers. You are the service delivery manager of the centre which hosts the servers. The centre is expected to be running 24x7. Five risk events have been identified and Table below shows the probability of each risk event happening and the corresponding business losses:

| Risk Event Description | Probability of Risk Event Happening | Loss of Revenue Per Day | Days for Recovery | EMV |
| --- | --- | --- | --- | --- |
| Power failure that affects all servers | 0.1% | $200,000 | 0.5 | 100 |
| Cluster of related servers breakdown | 0.3% | $50,000 | 2.0 | 300 |
| Data communication equipment breakdown | 2.0% | $20,000 | 1 | 400 |
| Electrical Fire | 0.005% | $300,000 | 5 | 75 |
| Cyber Security Threat – Denial of Service | 0.5% | $80,000 | 0.5 | 200 |

Calculate the Expected Monetary Value (EMV) for each risk event.

- Which risk event is the MOST important event that you want to manage? Justify your answer.

- Based on the EMV calculation, the data communication equipment breakdown is the most important risk to manage, as it has the highest expected monetary value. This means it poses the greatest expected financial impact on the project when considering both its likelihood and consequence.

- Identify a risk response strategy to manage the risk that you have identified in i. and describe one specific action you can use to carry out your strategy.

- Mitigate

- To reduce the probability of a data communication equipment breakdown, the company could implement a proactive maintenance schedule for all routers and switches. To reduce the impact, they could invest in redundant, backup communications lines that activate automatically if the primary line fails